## Slide 1
C/ISD: Douglas11
DC/ISD: Kelley05
Branch Chief: Cham18
Project Manager: Treva31
Feb 1, 2023
OSE ECB Projects Schedule - SecDevOps
ISD/ECB

## Slide 2
Align with ISD Current Priorities
  Technical Liabilities
  DIYOS RHEL-8 upgrade
  AutoM8 deployment
  DevOps Tools RHEL-8 upgrade
  Upgrades to EOL versions
    ServiceNOW
    Chef
    SonarQube
ISD Enterprise Capabilities Branch – Priorities

## Slide 3
ISD Enterprise Capabilities Branch – SecDevOps (SDO) Team
Name | Role | Resource | Onsite
Sarah01 | Project Manager | FTE | Mon-Th
Argha71 | Information System Security Officer | FTE | Mon-Fri
Brian28 | DevOps Engineer | FTE | N/A
Christopher28 | DevOps Engineer | FTE | N/A
Darrick07 | DevOps Engineer | FTE | N/A
George27 | DevOps Engineer | FTE | N/A
John32 | DevOps Engineer | FTE | Mon-Fri
Daniel (starts Feb 2023) | DevOps Engineer | FTE | N/A
Nathan15 | DevOps Engineer | FTE | N/A

## Slide 4
ISD Enterprise Capabilities Branch - ServiceNOW Team
Name | Role | Resource | Onsite
Ernest96 | Developer | FTE | Mon-Fri
Nancy74 | Developer | FTE | Tue, Wed, Thu

## Slide 5
CD
ISD Enterprise Capabilities Branch – 13 Enterprise Tools
Service
Management
ServiceNow
Bitwarden
Collaboration
Management
Confluence/Wiki
Jira
Development
DIYOS
Version Control
GitHub
Automated Build
Jenkins
Environment Configuration
AutoProv
Chef (Automate, Manage, Supermarket)
Nexus
CI
Quality & Security Management
SonarQube

## Slide 6
Enterprise Tools Release Status
logo | Tools | Current Version | Vendor Supported | Version Status | Upgrade Date | EOL Date | Impacted users
 | Bitwarden | 1.31.1 | No | EOL | N/A | 27Jul2020 | 30+
 | ServiceNow | Orlando | No | EOL | April 2023 | Q1 2021 | 730+
 | Chef Infra Client | 12.16.42 | No | EOL | May 2023 | 30Apr2021 | 
 | Chef Infra Server | 13.0.17 | No | EOL | May 2023 | 30Jun2021 | 
 | Chef Automate | 20210420090302 | No | Outdated | May 2023 | - | 430+ nodes
 | Chef Manage | 2.5.16 | No | 2023 Deprecation | May 2023 | TBD | 
 | Chef Supermarket | 3.3.1 | No | EOL | May 2023 | 2021 | 
 | PostgreSQL | 10 | No | EOL |  | 10Nov2022 | 
 | PostgreSQL | 11.13 | Yes | 2023 EOL |  | 9Nov2023 | 
 | SonarQube | 8.9.7 LTS | Yes | EOL soon | March 2023 | Dec 2022 | 164
 | JIRA | 8.15 LTS | Yes | 2023 EOL | TBD | 19Oct2023 | 339
 | GitHub | 3.6 | Yes | 2023 Deprecation | TBD | 16Aug2023 | 240
 | Confluence | 7.13.7 | Yes | 2023 EOL | TBD | 17Aug2023 | 730+
 | Jenkins | 2.356 | Yes | LTS v2.375 available | 7Feb2023 | - | 390+
 | Nexus Repository | 3.31.1 | Yes | Security Advisories | 24Feb2023 | - | 118
RED = EOL
Blue = near EOL

## Slide 7
Enterprise Tools Roadmap – Re-baseline Engineering
 | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  |  | Q4 2023 |  |  | Q1 2024 |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
DevOps Tools Tech Liabilities* |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIYOS RHEL8 upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AutoM8 replace AutoProv |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ServiceNOW Tech Liabilities & 2 Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Linux SSH Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Other Tools RHEL8 upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bitwarden SaaS Engineering |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef New Environments & Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef Manage Migration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GitLab Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A&A ATO Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mar 31
TBD
Deployment by Nov ’23
June 30
Mar 31
Jun 30
Baseline & Tech Liab - Feb 28 Rome Upgrade Tokyo/Utah Upgrade
Action Plan
*Tech Liabilities deployments: | 
2022 | 2023
18Nov Jenkins, Nexus and SonarQube 09Dec Jira and Confluence | 28Feb ServiceNOW 15Apr Chef Products (tentative)
Jull 30
Jul 30
IBC/RAQ
ISSM / ERB / AERB
Procurement
Engineering
IBC/PCR
Submission & Corrective Plans
April 15*
Chef
Jun 30
Feb 28
Tech Liab - Jan 31 Upgrade 1 – Apr 28 Upgrade 2 – Aug 31
Dec 31
= Current Timeline
= Prior Timeline
= New Project
= CURRENT MONTH

## Slide 8
 | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  |  | Q4 2023 |  |  | Q1 2024 |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
AutoM8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bitwarden |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Confluence |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIYOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GitHub |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Jenkins |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
JIRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nexus |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ServiceNow |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SonarQube |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PostgreSQL |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Enterprise Tools Roadmap - O&M
= Upgrade
= User License Maintenance
= Security Scans
= CURRENT MONTH
Migration to SaaS
Renew License
Two Upgrades
Upgrade
Chef Suprmkt
AutoProv Replacement
Upgrade
Renew License
All Impacted Tools
update
update
update
update
update
update
Renew License
Renew License
update
update
update
update

## Slide 9
SecDevOps Team – Projects 2023 Q2
Jan – March 2023
Project Stories/Tasks | Status | Target dates | Assigned Resource
Technical Liability - Chef Manage (TS-4377) | In-progress | 31Mar2023 | Brian28
Technical Liability - Chef Automate (TS-4378) | Not started | 31Mar2023 | Brian28
Technical Liability - Chef Supermarket (TS-4379) | Not started | 31Mar2023 | Brian28
DIYOS RHEL8 (TS-4156) | In-progress | 31Jan2023 - Advance User Pilot 31Mar2023 – General Deliverable | Darrick07
ServiceNOW baseline (TS-3713) | In-progress | 28Feb2023 | George27
December 2022 Shared Centos AMI (TS-4421 & TS-4422) | Not started | 18Jan2023 (Sprint 123) | George27
ServiceNOW PROD Cert (TS-4427) | In-progress | 18Jan2023 (Sprint 123) | George27
Script to automate service account passwords rotations (TS-4436) | In-progress | 08Feb2023 (Sprint 124) | Christopher28
Enable Backups for PROD servers – Chef Manage, Jenkins, Chef Supermarket | Completed | 08Feb2023 (Sprint 124) | Christopher28
Design Infrastructure Diagrams – Jira, Confluence, SonarQube (TS4495, TS-4496, TS-4501) | In-progress | 18Jan2023 (Sprint 123) | John32
ISSO activities (TS-4494) | In-progress | Continuous | Argha71
Research infrastructure/review vendor docs – Confluence, Jira (TS-4527,TS-4528) | In-progress | 18Jan2023 (Sprint 123) | Nathan15

## Slide 10
100+ Backlogs
Remediate Load Balancer for DevOps tools
Upgrades: Bitwarden, Chef, Nexus, ServiceNOW, SonarQube
Update Self-Signed Certs for SDO tools
Linux SSH Implementation
DIYOS Cookbook RHEL8 updates
User License Maintenance & Renewal
Splunk Reporting Review & Dashboard improvements
Automate EBS/RDS/Chef backups
Enhance CloudFormation templates
Improve DIYOS Spacewalk Failure Email
Jira integrations
SNOW enhancements & accreditation monitoring
DevOps Tools’ improvements
Automate DevOps Tools’ upgrade/patch deployments
Software recommendations: Nexus Firewall; Codeship; GitLab; Kanbanize; Monsido Web Accessibility

## Slide 11
Back up

## Slide 12
OSE SecDevOps – Resources
Project Stories/Tasks | Mar-Sept Sprints
Security Accreditation | 1 FTE
Installations/Upgrades/O&M | 3 FTE
Cyber Adversaries/ Security Remediations | 2 FTE
User Support/ Enhancements/Misc | 2 FTE
Engagements/ Software Analysis | -
Project Admin/Misc | 1 FTE
Total | 9
SecDevOps Team consist of 9 FTE (7 FTE engineers, 1 security advisor, 1 PM)

## Slide 13
Q4 2022 |  |  | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  |  | Q4 2023 |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Roadmap - Engagement
Edit 200+ Wiki pages
Tool surveys/evaluations
Map survey results to solutions
Brown Bag
Brown Bag
Brown Bag
= CURRENT MONTH

## Slide 14
Roadmap – Enhancements
Q1 2024
Oct
Nov
Dec
Q2 2024
Jan
Feb
Mar
Q3 2024
Apr
May
Jun
Q4 2024
Jul
Aug
Sep
Q4 2023
Jul
Aug
Sep
Auto-Create Team/Project specific:
Folders/views
Organizations
Groups
Auto-Assign User to Organization or Group
System Integration
Control User access
Associate AD Groups
Dev Team Features
Integration
Integration
Integration
Integration
Integration
Notes: Automation around configuration/management of tools
  - auto-creation of
    Jenkins folders/views for that project
    Team-specific GitHub organization
    Team/project-specific Chef organization
    Team/project-specific SonarQube group
  - auto-assign users to
    Chef organizations
    SonarQube groups
      Eliminate Chef/SonarQube Team Admin granting access
      use LDAP groups to assign users
AutoProv Auto-deployment in (a Cloud team suggestion)
  AWS
  Azure
  Google Cloud
Dev Team Features
  Associate AD Groups
    Confirm users are associated to a common AD Groups supporting permissions to tools
  Nexus Controls
    Configure to restrict access to other users’ work

## Slide 15
Roadmap – ServiceNow Engineering
Q3 2023
Apr
May
Jun
Q4 2023
Jul
Aug
Sep
Q1 2024
Oct
Nov
Dec
Q2 2024
Jan
Feb
Mar
Q2 2023
Jan
Feb
Mar
Workflow Improvement
System Integration
Integration
Integration
Notes: Automation around configuration/management of tools
  - auto-creation of
    Jenkins folders/views for that project
    Team-specific GitHub organization
    Team/project-specific Chef organization
    Team/project-specific SonarQube group
  - auto-assign users to
    Chef organizations
    SonarQube groups
      Eliminate Chef/SonarQube Team Admin granting access
      use LDAP groups to assign users
AutoProv Auto-deployment in (a Cloud team suggestion)
  AWS
  Azure
  Google Cloud
Dev Team Features
  Associate AD Groups
    Confirm users are associated to a common AD Groups supporting permissions to tools
  Nexus Controls
    Configure to restrict access to other users’ work

## Slide 16
Q4 2022
Oct
Nov
Dec
Roadmap - O&M – NOT READY
Upgrade = Upgrade Analysis
ULM = User License Maintenance
Scans = Security Scans
AutoProv
JIRA
Renew License
ULM
Scans
Confluence
Renew License
Security Update
DB
Q1 2023
Jan
Feb
Mar
Q2 2023
Apr
May
Jun
Q3 2023
Jul
Aug
Sep
Q4 2023
Oct
Nov
Dec
OpenShift
Scans
Bitwarden
Scans
ServiceNow
Scans
Jenkins
Scans
Scans
DIYOS
SonarQube
Scans
Scans
Nexus
Scans
Scans
Chef
Renew License
Scans
Scans
GitHub
Renew License
ULM
Scans
Scans
License
ULM
Scans
Scans
Transfer 2 ESB
Scans
Patch
Patch
Log4j Patch
Patch
Scans
Scans
Log4j Patch
TODAY
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Decommission
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
ULM
ULM
ULM
ULM
ULM
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Scans
Scans
Renew License
ULM

## Slide 17
TODAY
New Work Activities - OLD
 | Q3 2022 |  |  | Q4 2022 |  |  | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  | 
 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
ADFS Transition (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AutoM8 (Development) (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RHEL8 Install Baseline* (all) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DevOps Tools in RHEL8 (2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deploy DIYOS in RHEL8 (all) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TLS/SSL Remediation (3) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef Upgrade (all) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef Migration* (all) (Manage > Automate) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Baseline Deployment (all) Methodology for DevOps |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Accessibility Tools in Nexus (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SSH Engineering Work (ESB) (?) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Security Controls for Accreditation (all) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GitLab Evaluation* (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Accessibility Testing (?) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migrate toward Cloud (2) Services / Managed Services* |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Engineering . Transition
Engineering . Transition
Deployment
Dev
Test
PROD
Target
Target
Target
Target
Target
Target
Ongoing Work
RHEL8 Install Baseline – pending discussion with ESB
Chef Manage EOL extended to at least 30 Nov 2023 – migration will move out
GitLab Evaluation – no timeline yet
Migrate to Cloud Services / Managed Services – no timeline yet; requires investigation
6/30
6/30
EOL Nov 23
CentOS Decommission 6/30

## Slide 18
Roadmap - O&M – old
Upgrade = Upgrade Analysis
ULM = User License Maintenance
Scans = Security Scans
AutoProv
JIRA
Confluence
Renew License
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
OpenShift
Bitwarden
ServiceNow
Jenkins
DIYOS
SonarQube
Nexus
Chef
GitHub
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Decommission
Scans
Scans
Scans
ULM
ULM
ULM
ULM
ULM
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Scans
Scans
Renew License
ULM
Replacement/Decommission
Upgrade
Upgrade
TODAY
Q2 2023
Jan
Feb
Mar
Q3 2023
Apr
May
Jun
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Scans
Upgrade
Scans
Upgrade
Scans
Scans

## Slide 19
 | Q3 2022 |  |  | Q4 2022 |  |  | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  | 
 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
AutoM8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bitwarden |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chef |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Confluence |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIYOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GitHub |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Jenkins |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
JIRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nexus |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
OpenShift |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ServiceNow |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SonarQube |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Scans
Roadmap - O&M
= Upgrade/Upgrade Analysis
= User License Maintenance
= Security Scans
Renew License
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Decommission
Scans
ULM
ULM
Upgrade
Upgrade
Upgrade
Upgrade
Scans
Scans
Renew License
Upgrade
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Scans
Scans
Scans
ULM
ULM
ULM
ULM
ULM
ULM
Scans
Upgrade
Scans
Upgrade
Upgrade
TODAY
Upgrade
Scans
Upgrade
Upgrade
Upgrade
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans

## Slide 20
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
Q2 2023
Jan
Feb
Mar
Roadmap - Upgrades
Q3 2023
Apr
May
Jun
Q4 2023
Jul
Aug
Sep
Q1 2024
Oct
Nov
Dec
GitHub
Jenkins
Nexus
SonarQube
Chef Infra.
Chef Auto.
Chef Manage
Chef Super.
Confluence
Jira
ServiceNow
Bitwarden
DIYOS
End of Life (version as of Sep 2022)
Complete
Major Upgrade
Minor Upgrade
3.37.x
2.5
8.20.11
3.6.0
2.23
14.4.4
migrate
Rome
TODAY
3.5.4
2.356
REHL 8

## Slide 21
Q4 2021
Jul
Aug
Sep
Q1 2022
Oct
Nov
Dec
Q2 2022
Jan
Feb
Mar
Roadmap - Upgrades
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
AutoProv
GitHub
Jenkins
Nexus
SonarQube
Chef Infra.
Chef Auto.
Chef Manage
Chef Super.
Confluence
Jira
ServiceNow
Bitwarden
DIYOS
OpenShift
End of Life (version as of Nov 2021)
Complete
Major Upgrade
Minor Upgrade
3.37.x
2.2.1
3.31.1
2.11.7
2021..
8.9
3.0.7
7.19
4.9
2.5
2.322
3.11.420
8.20.11
PostgreSQL 11.13
3.6.0
20211216b1
20211213b1
2.23
14.4.4
migrate
8.9.6
Rome
TODAY
PostgreSQL 11.13.
3.5.4
2.356

## Slide 22
Roadmap - Engagement
Q4 2023
Jul
Aug
Sep
Q3 2023
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
Q2 2023
Jan
Feb
Mar
TODAY
Edit 200+ Wiki pages
Tool surveys/evaluations
Map survey results to solutions
Brown Bag
Brown Bag
Brown Bag

## Slide 23
ISD Enterprise Capabilities Branch
Apr – June 2023
Project Stories/Tasks | Status | Target dates | Assigned Resource
Technical Debt – ServiceNow (TS-4382) | Not started | TBD | George27 Nathan15
SSL/TLS Load Balancer Encryption Updates (TS-4327, TS-4326, TS-4320, TS-4319, TS-4318, TS-4317, TS-4316) | Not started | TBD | 
DevOps Tools to RHEL8 | Not started | TBD | 
SSH Implementation | Not started | TBD | 
AutoM8 - AutoProv replacement | Not started | TBD |