## Slide 1
C/ISD: Douglas11
DC/ISD: Kelley05
Branch Chief: Cham18
Project Manager: Treva31
March 16, 2022
OSE Enterprise Tools Integration Schedule
ISD/ECB

## Slide 2
CD
ISD Enterprise Capabilities Branch - Enterprise Tools
Service
Management
ServiceNow
Bitwarden
Collaboration
Management
Confluence/Wiki
Jira
Development
DIYOS
OpenShift
Version Control
GitHub
Automated Build
Jenkins
Environment Configuration
AutoProv
Chef
Nexus
CI
Quality & Security Management
SonarQube
SecDevOps Tool Suite

## Slide 3
The following roadmaps provide estimated timelines for routine O&M, user engaging, and enhancing the OSE SecDevOps Tools
  Roadmaps
    Slide 5 – O&M
    Slide 6 – Upgrades
    Slide 7 – Accreditation
    Slide 9 – Enhancements
    Slide 11 – Engagements
OSE SecDevOps Tools – Schedule

## Slide 4
Roadmap - O&M Objectives
VSR = Vendor Supported Release
LR = Latest Release
All Tools operate at the latest vendor release version
  Quarterly Software Analysis identifying upgrade requirements to latest version and deployment (Gray Timelines)
Provide Security Scans as required by Security
  Every 120-days archive Security Scans in Roadrunner (Blue Timelines)
Maintain User Licenses
  Conduct Quarterly analysis to release inactive user accounts from Jira and GitHub to guarantee Dev on-boarding and reduce cost (Violet Timelines)
Obtain Security Accreditation
  ATD completion indicated with Red timelines
  ATO indicated with Yellow timelines

## Slide 5
Q1 2022
Oct
Nov
Dec
Roadmap - O&M
Upgrade = Upgrade Analysis
ULM = User License Maintenance
AutoProv
JIRA
Renew License
ULM
Scans
Confluence
Renew License
Security Update
DB
Q2 2022
Jan
Feb
Mar
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
OpenShift
Scans
Bitwarden
Scans
ServiceNow
Scans
Jenkins
Scans
Scans
DIYOS
SonarQube
Scans
Scans
Nexus
Scans
Scans
Chef
Renew License
Scans
Scans
GitHub
Renew License
ULM
Scans
Scans
License
ULM
Scans
Scans
Transfer 2 ESB
Scans
Patch
Patch
Log4j Patch
Renew License
Patch
Scans
Scans
Log4j Patch
TODAY
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
Scans
ULM
ULM
ULM
ULM
ULM
ULM
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade
Upgrade

## Slide 6
Q4 2021
Jul
Aug
Sep
Q1 2022
Oct
Nov
Dec
Q2 2022
Jan
Feb
Mar
Roadmap - Upgrades
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Q1 2023
Oct
Nov
Dec
AutoProv
GitHub
Jenkins
Nexus
SonarQube
Chef Infra.
Chef Auto.
Chef Manage
Chef Super.
Confluence
Jira
ServiceNow
Bitwarden (Serv)
Bitwarden (Web)
DIYOS
OpenShift
End of Life (version as of Nov 2021)
Complete
Major Upgrade
Minor Upgrade
3.37.x
Once complete, the full SecDevOps ATO can proceed (everything here, except ServiceNow and OpenShift)
2.2.1
3.31.1
2.11.7
2021..
8.9
3.0.7
Rome
7.13
8.7
4.7
2.5
2.322
3.11.420
8.13
PostgreSQL 11.13
3.2.x
3.0.7
PostgreSQL 11.13
20211216b1
20211213b1
1.43
2.23
14.4.4
migrate
TODAY
8.9.6

## Slide 7
Q4 2021
Jul
Aug
Sep
ServiceNow
OpenShift
Roadmap – Accreditation
SecDevOps
Q1 2022
Oct
Nov
Dec
Q2 2022
Jan
Feb
Mar
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
ATO
ATO 18-month term
ATO 3yr term
ATD
TODAY

## Slide 8
Roadmap – Enhancements Objectives
Provide easy access to the Code Management and Development Tools
  Assigning users to AD Groups that grant access to specific tools to
    auto-create of folders/teams/projects
    auto-assignment of project/organizations
    Control access
Integration of Code Management and Development Tools
Leveraging Tools to meet stakeholder requirements

## Slide 9
Roadmap – Enhancements
Q1 2023
Oct
Nov
Dec
Q2 2023
Jan
Feb
Mar
Q3 2023
Apr
May
Jun
Q4 2023
Jul
Aug
Sep
Q4 2022
Jul
Aug
Sep
Auto-Create Team/Project specific:
Folders/views
Organizations
Groups
Auto-Assign User to Organization or Group
System Integration
Control User access
Associate AD Groups
Dev Team Features
Integration
Integration
Integration
Integration
Integration
Notes: Automation around configuration/management of tools
  - auto-creation of
    Jenkins folders/views for that project
    Team-specific GitHub organization
    Team/project-specific Chef organization
    Team/project-specific SonarQube group
  - auto-assign users to
    Chef organizations
    SonarQube groups
      Eliminate Chef/SonarQube Team Admin granting access
      use LDAP groups to assign users
AutoProv Auto-deployment in (a Cloud team suggestion)
  AWS
  Azure
  Google Cloud
Dev Team Features
  Associate AD Groups
    Confirm users are associated to a common AD Groups supporting permissions to tools
  Nexus Controls
    Configure to restrict access to other users’ work

## Slide 10
Roadmap – Engagement Objectives
Inform OSE developer of the 12 Enterprise Tools capable to assist with their Mission application development efforts
Formalize the 12 Enterprise Tools as a centralized SecDevOps tool suite supporting CI/CD framework
Collect insight to implement tools that effectively support the features and capabilities desired in development

## Slide 11
Roadmap - Engagement
Q4 2021
Jul
Aug
Sep
Q1 2022
Oct
Nov
Dec
Q2 2022
Jan
Feb
Mar
Q3 2022
Apr
May
Jun
Q4 2022
Jul
Aug
Sep
Software Tracking System
Icon design & deployment
Edit 200+ Wiki pages
Tool surveys/evaluations
Map survey results to solutions
Brown Bag
TODAY
Brown Bag

## Slide 12
ECB Backlog / Initiatives (Priorities in order)
Bugs – Nexus, Chef, Jira
Upgrades – Jira, Chef, ServiceNow, others
Accreditation
Remediate Security Recommendations
Linux SSH Implementation
Bitwarden decommission
Improvements
  Pipelines & CloudFormations
  Automate backups, snapshots & configuration scaling
  Tool enhancements
Software Analysis
  Nexus Firewall
  Alternatives to Jira, GitHub, Jenkins, etc
  Accessibility Testing Tools
OSE SecDevOps – Backlog

## Slide 13
OSE SecDevOps Suite – Future
Engage SecDevOps Suite as a centralized CI/CD solution for OSE
Develop enhancements and/or deploy new capabilities to meet OSE Dev Community demands