## Slide 1
C/ISD: Douglas11
DC/ISD: Kelley05
Branch Chief: Cham18
Project Manager: Treva31
Nov 3, 2021
Enterprise Capabilities Branch Project Status Report (PSR)
18-Oct-21 through 29-Oct-21

## Slide 2
PSR Agenda
Reorganization
Contractual Transition
A&A status
Upgrades status – Critical, All
OpenShift
Enterprise Tools
ServiceNow
InfoSec
R&D
Backlog

## Slide 3
MTG Reorganization
Structured within Infrastructure Services Division (ISD)
ISD leadership
  Douglas11, Chief
  Kelley05, Deputy Chief
ISD Branch - Enterprise Capabilities
  Enterprise Tools
  Identity Access Management
  Information Security (InfoSec) Services
  OpenShift
  ServiceNow
Enterprise Capabilities leadership
  Cham18, Branch Chief
  Angela38, PM – Identity Access Mgmt & InfoSec Services
  Treva31, PM – Enterprise Tools, OpenShift, ServiceNow

## Slide 4
Contractual Transition
Black Panther Contract
Awarded - Aysmmetrik
Transition/Knowledge Transfer
  Enterprise Tools Team
  ServiceNow Team
Transition leadership
  Treva31, Gov’t
  Isaac91, Aesir
  Karen45, Asymmetrik
  Eric55, Asymmetrik

## Slide 5
OSE Enterprise Tools - ATO Status
03-Nov-21
 |  | A & A RMF Process |  |  |  |  |  |  |  | 
Project | Status | STEP 0 registration | STEP 1 categorize | STEP 2 select | STEP 3 implement | STEP 4 assess | STEP 5 authorization | STEP 6 monitoring | % Complete | Accreditation Expiration Date
SecDevOps includes 12 tools | ATD | X | X | X | X |  |  |  | 25% | 23Oct22
ServiceNow | ATO | X | X | X | X | X | X | X | 76% | 25Aug24
OpenShift | ATO | X | X | X | X | X | X | X | 71% | 17Feb23
Updated |  | ATO Expired |  | ATO Expires in 3 months | 

## Slide 6
OSE SecDevOps Tools Status - Critical Upgrades
Step | Description | Nexus | DIYOS | AutoProv | SonarQube | GitHub | Confluence & PostgreSQL | Jira & PostgreSQL | SNow | Jenkins & Java 11 | Bit Server & Web
1 | Review release notes / security relevant changes | X | X | X | X | N/A | current | current | X | N/A | N/A
2 | Plan for upgrade identifying versions & dependencies | X | X | X | X | N/A |  |  | X | X | current
3* | Obtain approval from ISSM/ISSE confirming security changes are N/A | X | X | X | X | X |  |  | X | X | 
4^ | Submit P&SC ticket for software authorization | X | N/A | N/A | X | X |  |  | X | X | 
5^ | Submit ServiceNow ticket to obtain the software | X | N/A | N/A | X | X |  |  | X | X | 
6 | Obtain the software from either DCB, or alternate | X | N/A | N/A | X | X |  |  | current | current | 
7 | Perform the Upgrade in DEV/TEST/Stage | DEV & TEST | N/A | DEV & TEST | DEV & TEST | DEV & TEST | DEV & TEST | TEST | Stage, DEV & TEST | DEV & TEST | TEST
8 | Submit ServiceNow ORB Change Request for PROD | X | X | X | X | X |  |  |  |  | 
9 | Submit a Maintenance and/or Tech Note | X | X | X | X | X |  |  |  |  | 
10 | Perform the Upgrade to PROD | X | X | X | X | X |  |  |  |  | 
11 | Request Security Scans of DEV/TEST/PROD | X | X | X | X |  |  |  |  |  | 
12 | Provide ISSM/ISSE with POA&Ms | Current | current | current | current |  |  |  |  |  | 
* Step 3 is not applicable for minor version updates. ^ Step 4 & 5 are not applicable if software version is registered in P&SC.
Tools with current version at EOL or enforced by JetBrains decommission
n = Prioritization change
03-Nov-21

## Slide 7
OSE SecDevOps Tools Status – All Upgrades
03-Nov-21
Priority | Tools | Current Version (CV) | CV Supported by Vendor | Upgrade version | Upgrade Driver | ISSM Approval date | Upgrade Process per Slide 6 | Upgrade Completed
2 | Nexus | 3.21.2 | No | 3.31.1 | ATO | 6July21 | Step 11 | 22July21
3 | DIYOS | 2.6.1 | Yes | 2.11.7 | JetBrains | 22July21 | Step 12 | 30Jul21
4 | Linux AutoProv | 20201125b1 | Yes | 20210903b0 | JetBrains | n/a | Step 12 | 14Sep21
5 | SonarQube | 8 | No | 8.9 | ATO | n/a | Step 11 | 23Sep21
6 | GitHub | 2.22.17 | Yes | 3.0.7 | EOL* | 22Sep21 | Step 11 | 02Nov21
7 | Confluence | 6.15.6 | No | 7.13 | ATO |  | Step 2 | 
8 | JIRA | 8.7.1* | Yes | 8.13 LTS | EOL* | n/a | Step 1 | 
8 | ServiceNow | Orlando | Yes | Rome | EOL |  | Step 6 | 
9 | Jenkins | 2.249.1 | No | 2.303.1 | ATO | n/a | Step 7 | 
9 | OpenShift | 3.11.420* | Yes | 4.7 | EOL* |  | Step 1 | 
10 | Bitwarden Server | 1.31.1 | No | 1.43.0 | ATO | n/a | Step 2 | 
10 | Bitwarden Web | 2.11.0 | No | 2.23.0 | ATO | n/a | Step 2 | 
12 | Chef Infra Server | 13.0.17 | Yes | 14.4.4 | outdated |  |  | 
12 | Chef Automate | 20210420090302 | Yes | 20210713164523 | outdated |  |  | 
12 | Chef Manage | 2.5.16 | Yes | Migrate to Chef Automate | EOL* |  |  | 
12 | Chef Supermarket | 3.3.1 | Yes | 3.4.13 | Outdated |  |  | 
*reaches EOL: GitHub 2.22 on 23-Sep-21; Jira 8.7 on 03-Feb-22; OpenShift 3.11 on 22-Jun-22; Chef Manage on 31-Dec-22
n = Prioritization change

## Slide 8
OSE Enterprise Tools O&M
03-Nov-21
Chart edited in the Enterprise Tools roadmap PPT, located in this folder: https://opensourcegov.sharepoint.com/:f:/s/toolsandservices/EgGoTX9DzkhHjsgbtyjQ-rsB0he1uGHuCdyJQq9hli6PdA?e=WAb0BC

## Slide 9
OpenShift for OSE
Schedule
Major Concern |  | Minor Concern |  | On Target |  | Completed | 
Accomplishments
Overview
OpenShift is a container hosting platform providing an easy way for missions to host, scale, and secure workloads. Our goal is to reduce time-to-mission by removing the operational overhead and friction for common tasks like configuring application environments, building fault tolerance, and scaling workloads.
MTG Lead: Treva31
Team: Ashley95, Kevin76, and Dirk33
Users: 40+
User Engagement Method: Teams, Email, Phone, ServiceNow
Partner(s): MTG, OSE
Planned Activities
03-Nov-21
Overall Status
Constraints
Milestones | Planned Start Date | Actual Start Date | End Date | Status
(Upgrade) Initial briefing for security and technical stakeholders | Jan-Mar ’21 |  |  | 
(Upgrade) Deploy OpenShift v4 to FWD Lab | Apr-Jun ’21 | Sep ‘21 | Sep ’21 | 
(Upgrade) Deploy prototype to customer environments | Sep-Dec ’21 | Sep ‘21 | TBD | 
(Upgrade) Coordinate with security to execute scans and update docs | Jan-Feb ’22 | -- | -- | 
(Upgrade) Conduct user acceptance testing | Mar-Apr ’22 | -- | -- | 
(Upgrade) Transition users and workloads | May ’22 | -- | -- | 
(Upgrade) Installed kube2iam in Test VPC and verified functionality.
(Upgrade) Completed initial install of OCP4 in Development VPC.
(Upgrade) Perform kube2iam install in Production.
(Upgrade) Create custom Red Hat CoreOS AMI for OCP4.
(O&M) November patching will be completed by COB 11/17/21.
Assumptions:
N/A
Dependencies:
N/A
Risks:
(Upgrade) DeveloperFull IAM role does not appear to have all needed permissions for OCP4 install; opened ticket (OSTK0034812) with cloud team to investigate.

## Slide 10
OSE Enterprise Tools O&M
Schedule
Major Concern |  | Minor Concern |  | On Target |  | Completed | 
Accomplishments
Constraints
Overview Continuous operations and maintenance (O&M) support for the 12 Enterprise Tools that assist with developing, managing, and delivering OSINT solutions.
MTG Lead: Treva31
Team: Isaac91, Spencer08, Wesley74, Victoria63
Users: 600+
User Engagement Method: Phone, Email, Teams, ServiceNow
Partner(s): MTG, ISSM, DVV, OMA
Planned Activities
03-Nov-21
Overall Status
O&M Roadmap
Milestones | Planned Start Date | Actual Start Date | Projected End Date | Status
A&A ATO | 03Nov20 | 03Nov20 | TBD | 
RR PROD Security Scans | 16Apr21 | 16Apr21 | 30Sep21 | 
Update SonarQube | 09Aug21 | 10Aug21 | 23Sep21 | 
PostgreSQL Update | 15Oct21 | 15Oct21 | 10Nov21 | 
Security Update Confluence | 15Aug21 | 15Aug21 | 26Oct21 | 
Upgrade GitHub | 22Sep21 | 15Oct21 | 30Nov21 | 
Upgrade Confluence | 06Dec21 | 1Nov21 | 31Jan22 | 
Update Jira | 01June21 | TBD | 01Mar22 | 
License: GitHub | 29June21 | 29June21 | 08Nov21 | 
Deployed: 26-Oct Confluence Security Patch
Completed: 29-Oct Migration of Chef Supermarket to a new instance (due 31 Oct)
Deployed: 02-Nov GitHub upgrade from v2.22.17 to v3.0.7
Deployed: 02-Nov PostgreSQL (for Jira & Confluence) upgrade from v9.6.22 to v11.13
Recevied: ATD for the new SecDevOps single A&A Project
Completed weekly audit review of TNS Splunk logs
Updated Roadmap to account for Transition Impacts (1 month)
Complete weekly audit review of TNS Splunk logs
Confluence v7.13 Upgrade Efforts
Participate in Knowledge Transfer / TEMs with Black Panther team
GitHub License: Receive temporary key if long term is not ready yet, as the current license expires 8 Nov (working with Brett H on this)
Assumptions:
ATO can not proceed until all tools are at least on vendor-supported versions (6 remaining to upgrade)
Dependencies:
Temporary (and long term) GitHub License via procurement
Risks:
GitHub will provide temp license, but we are getting close

## Slide 11
OSE ServiceNow
Schedule
Overview
Enterprise IT Service Management (ITSM) platform that automates IT Business Management activities for OSE, replacing the legacy Supportworks.
MTG Lead: Treva31
Team: Isaac91, Max87, Ernest96, Zechary11, Wesley74, Victoria63
Users: 400+
User Engagement Method: ServiceNow User Group, Sprint Planning
Partner(s): MTG
Major Concern |  | Minor Concern |  | On Target |  | Completed | 
Accomplishments
Constraints
Overall Status
Planned Activities
03-Nov-21
Roadmap
Milestones | Planning Date | Start Date | End Date | Status
A&A ATO | 19Apr21 | 24May21 | 31Aug21 | 
Requirement Intake | 18Aug21 | 18Aug21 | 12Oct21 | 
AERB request | 12Aug21 | 16Aug21 | 23Nov21 | 
Upgrade to Quebec | 22Jun21 | 29Jun21 | Mar‘22 | 
Automated Testing | 29Jul21 | 29Jul21 | TBD | 
Casper Account requests | 01Jul21 | 05Jul21 | TBD | 
Automate Cloud | 29Jul21 | 02Aug21 | TBD | 
Performance Analytics | 12Aug21 | 30Aug21 | 9Nov21 | 
Assumptions:
Dependencies:
ISD/PSB for Cloud API modifications and testing
Risks:
Prep changes in system for BOSD shift to ISD/ECB
Participate in Transition/TEMs with Black Panther as necessary
Deploy AERB once MTG TD has hosted demo to team and stakeholders
Coordinate with ISD/PSB to update and test Cloud API integration
Remove ServiceNow Form/Workflow for Enhancements
Focus on the PROD clone (to TEST) per ISSM approval
Finalize updated CM Plan approval
Continue Dashboards and Reporting (i.e., performance analytics)
Continue prep for Upgrade to Rome
Deploy Sprint 29 to PROD on 9Nov
Provide demo to ISD new folks on 10 Nov
Hosted Sprint 29 Demo/Review/Planning sessions with stakeholders, and coordinated user acceptance testing (UAT)
Deployed Sprint 28 to PROD on 26 October
  Knowledge Article, update to My Requests list, update to DNS Form, update to ORB pre-approved list, updates to Emergency ORB email notifications
Patched PROD servers with latest AMI
Prep for deployment: Dashboards (Iteration 1), DXD/COSO group for ATOM tix

## Slide 12
OSE InfoSec
Schedule
Overview
MTG Lead: Angela33
Team:
Users:
User Engagement Method:
Partner(s): MTG
Major Concern |  | Minor Concern |  | On Target |  | Completed | 
Accomplishments
Constraints
Overall Status
Planned Activities
03-Nov-21
Milestones | Planning Date | Start Date | End Date | Status
A&A ATO | 19Apr21 | 24May21 | 31Aug21 | 
Requirement Intake | 18Aug21 | 18Aug21 | 12Oct21 | 
AERB request | 12Aug21 | 16Aug21 | 9Nov21 | 
Upgrade to Quebec | 22Jun21 | 29Jun21 | Feb ‘22 | 
Automated Testing | 29Jul21 | 29Jul21 | TBD | 
Casper Account requests | 01Jul21 | 05Jul21 | TBD | 
Automate Cloud | 29Jul21 | 02Aug21 | TBD | 
Performance Analytics | 12Aug21 | 30Aug21 | 9Nov21 | 
Assumptions:
Dependencies:
Risks:

## Slide 13
OSE R&D
Schedule
Overview
TBD.
MTG Lead: TBD
Team:
Users:
User Engagement Method:
Partner(s): MTG
Major Concern |  | Minor Concern |  | On Target |  | Completed | 
Accomplishments
Constraints
Overall Status
Planned Activities
03-Nov-21
Milestones | Planning Date | Start Date | End Date | Status
A&A ATO | 19Apr21 | 24May21 | 31Aug21 | 
Requirement Intake | 18Aug21 | 18Aug21 | 12Oct21 | 
AERB request | 12Aug21 | 16Aug21 | 9Nov21 | 
Upgrade to Quebec | 22Jun21 | 29Jun21 | Feb ‘22 | 
Automated Testing | 29Jul21 | 29Jul21 | TBD | 
Casper Account requests | 01Jul21 | 05Jul21 | TBD | 
Automate Cloud | 29Jul21 | 02Aug21 | TBD | 
Performance Analytics | 12Aug21 | 30Aug21 | 9Nov21 | 
Assumptions:
Dependencies:
Risks:

## Slide 14
SDO Project Backlog
Overview
Support and Advance Software Delivery and Operation (SDO) Strategy, Objectives, and Roadmaps
MTG Lead: Cham18
Team: treva31 and Isaac91
06-Oct-21
Projects | Description | Mission Impact | Status
SDO Strategy & Roadmap | Engage with developers' community and provide SDO and Enterprise Tools to our developers to achieve their delivery for the OSE missions. | TBD | In Progress
SDO & Enterprise Tools’ Research and Development (R&D) | This effort is to preform market research for of all commercial companies that have the capability of advancing SDO & Enterprise Tools and empower our developers to achieve more with OSE objectives and deliveries | Ensure OSE is getting best value product to meet current needs. Researching companies with SDO and Enterprise Tools capability | Due to no resource, on hold
CHiPs | Provide updates to MTG Leadership regarding BOSD’s assigned cyber implementation steps. Work in coordination with ISD and ISSM teams to close identified gaps. | Improve the overall security of the OSE Network. | Working with MTG Technical Director to provide updates as needed (Closed as of Sept 25)
Survey / Communication Forum | Engage with Developers and provide better solutions to their requirements |  | 
Metrics Efforts |  |  | 
ServiceNow Integration | TBD | TBD | Explored with JIRA and SN capabilities using within AWS Services
Tool Evaluation | Analyze the functionality of the current pipeline and the extent of use (capture the as-is state) and conduct an assessment of available tools including recommendations for future use (potential to-be state) |  | Under evaluation