## Slide 1
OpenShift for OSE: Decommission Plan
ISD Enterprise Capabilities Branch
C/ISD: Douglas11
DC/ISD: Kelley05
Branch Chief: Cham18
Project Manager: Treva31
May 26, 2022

## Slide 2
Decommission Plan Timeline – ECB Staff
Jun 2022
Jul 2022
Aug 2022
Sep 2022
  11Jul22 Schedule end date/time with Security, FSB, ESB/OSE Service
  2nd Tech Note decommission reminder
    01Sept22 Final Tech Note decommission reminder
    12Sept22 Maintenance Notification
    14Sept22 Confirm decommission completion with OpenShift Team, Security, FSB
    02Jun22 1st Tech Note decommission notification
  08Aug22
    3rd Tech Note decommission reminder
    23Aug22
    Submit ORB for decommission maintenance

## Slide 3
13Sep22
Complete Decommission maintenance:
Steps on slide 4
Decommission Plan Timeline – OpenShift Team
Jun 2022
Jul 2022
Aug 2022
Sep 2022
  02Jun22 Inform System Owners of OpenShift integration points to plan/modify as needed
14Jul22 Confirm decommission end date and requirements with Security, FSB, and ESB
22Aug22 Provide ORB data to Staff
23Aug22
Submit SN requests:
  AWS Account Management
  VPC Network Service
Obtain data management requirements concurrence
Dates contingent on Plan approval

## Slide 4
Backup Artifacts and migrate any projects (OOSE)
Cleanup all EC2 instances, RDS, and S3 resources (OOSE)
Execute automation script to disable OpenShift workloads (OOSE)
Terminate OpenShift core (OOSE)
Shutdown the Windows or Linux VMs/DNS/LDAP (OOSE)
Delete Storage Systems (OOSE)
Disable AWS Cloud and VPC Services (FSB)
Network and Splunk integration cleanup (FSB)
Archive Security Decommission Checklist (OOSE)
Decommission Maintenance – Steps

## Slide 5
Hello OSN Users,
OpenShift for OSE will be decommissioned COB 13Sep22. Prior to this date, MTG recommends code developed, managed, and/or hosted on OpenShift for OSE be transferred to an alternative platform over the next 4-months. As a result of this decommission, new projects onboarding has ceased.
Additional reminder notifications will be emailed monthly prior to the decommission deadline, COB 13Sep22.
Please forward any questions, comments, or additional information requests to ISD_ECB_STAFF.
Regards,
ECB Staff
Decommission Plan – 1st Tech Note Notification

## Slide 6
Hello OSN Users,
As a reminder of OpenShift for OSE decommission COB 13Sep22, please confirm code developed, managed, and/or hosted on OpenShift for OSE is transferred to an alternative platform prior to this date.
Please forward additional information requests to ISD_ECB_STAFF.
Regards,
ECB Staff
Decommission Plan – Monthly Tech Note Notification

## Slide 7
Maintenance - OpenShift Decommission | 13 September 2022
OpenShift for OSE will be decommissioned from OSN network on 13Sep22.
Transference of code developed, managed, and/or hosted on OpenShift for OSE should be complete.
If you have questions or concerns, please contact the OSE Service Desk:
• 703-874-7000, option 4
• OSE_SERVICEDESK_OPS@opensource.gov.
Decommission Plan – Maintenance Notification