## Stories
Stories ID | Stories | Server pts. | Client pts. | In Team Review | In UX | In Dev | # To Dos | # To Dos done | % Dev complete | In Testing | # Test cases | # Test cases done | % Testing complete | In Acceptance | In Production | Facet | App section | Epics | Blocks release | Sprint | Release seq. no. | Blocking stories | So that | FhabTask | P[?] | Server eng. tasks | Client eng. tasks | Notes | FhabURL | Notes
S110 | authorized user provides user name and password to access change request tool | 10 | 8 | done | done | done | 25 | 25 | 100% | in-progress | 10 | 5 | 50% |  |  | F010: sign-in/authenicate credentials | AP010: Log in/out | E210: Tool Access |  | SP010: Account Log-In; SP020: Account log-in authenication; SP040: Request Log-In credentials | 4
S120 | tool detects the device rendering the log in page |  |  | in-progress | n/a |  | 1 | 0 | 0% |  | 1 | 0 | 0% |  |  | F020: device detection | AP010: Log in/out | E210: Tool Access |  | SP030: URL device detention | 4
S130 | log in authentication grants access to tool's welcome screen | 6 | 6 | done | done | in-progress | 10 | 5 | 50% |  | 5 | 2 | 40% |  |  | F030: welcome screen | AP010: Log in/out | E210: Tool Access |  | SP010: Account Log-In; SP020: Account log-in authenication; SP030: URL device detention; SP040: Request Log-In credentials | 3
S140 | user specifies two-factor authenication type: text to mobile phone | 6 | 6 | done | in-progress | in-progress | 1 | 0 | 0% |  | 1 | 0 | 0% |  |  | F040: two-factor authority, mobile or email | AP010: Log in/out | E210: Tool Access |  | SP010: Account Log-In; SP020: Account log-in authenication; SP040: Request Log-In credentials | 5
S145 | user specifies two-factor authenication type: email to account on file |  |  | in-progress |  |  | 1 | 0 | 0% |  | 1 | 0 | 0% |  |  | F040: two-factor authority, mobile or email | AP010: Log in/out | E210: Tool Access |  |  | 100
S150 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  | F050: request access credentials | AP010: Log in/out | E210: Tool Access |  |  | 1
S160 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  | F060: sign-out/kill session | AP010: Log in/out | E210: Tool Access |  |  | 2
S170 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP010: Log in/out | E210: Tool Access |  |  | 2
S180 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP020: account profile | E220: Review or Maintain account profile |  |  | 3
S190 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP020: account profile | E220: Review or Maintain account profile |  |  | 2
S200 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP020: account profile | E220: Review or Maintain account profile |  |  | 3
S210 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP020: account profile | E220: Review or Maintain account profile |  |  | 5
S220 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP030: website profile | E230: Review sitemap |  |  | 4
S230 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E230: Review sitemap |  |  | 100
S240 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation |  |  | 100
S250 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation
S260 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation; E260: Change request completed & account billed
S270 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation
S280 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation
S290 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP040: change request | E240: Change request creation
S300 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP050: change request approval | E250: Change request status
S310 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP050: change request approval | E250: Change request status
S320 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP060: change requested posted | E260: Change request completed & account billed
S330 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP060: change requested posted | E260: Change request completed & account billed
S340 | [8 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  | AP060: change requested posted | E260: Change request completed & account billed

## Epics
Epics ID | Epics | release milestones | Description | No. stories | Seq. no. | Blocked by (Epic) | Sprints | Rob est. | Server pts. | Client pts. | No. open stories
E210 | Tool Access | MS010: Client Log-In; MS020: Client Log-In Authenication; MS030: Client Log-In request credentials; MS040: URL device detention; MS110: Full release |  |  |  |  | SP010: Account Log-In; SP020: Account log-in authenication; SP030: URL device detention; SP040: Request Log-In credentials | M | 3 | 2 | 0
E220 | Review or Maintain account profile | MS050: Account Profile Maintenance; MS110: Full release |  |  |  |  | SP050: Account Profile Maintenance - general; SP060: Account Profile Maintenance - billing; SP070: Account Profile Maintenance - change request history | M | 1 | 3 | 1
E230 | Review sitemap | MS060: Account Sitemap; MS110: Full release |  |  |  |  | SP080: Account Sitemap
E240 | Change request creation | MS070: Change Request; MS080: Change Request instructions; MS110: Full release |  |  |  |  | SP090: Change Request - add content; SP100: Change Request - delete/remove content; SP110: Change Request - update content; SP120: Change Request instructions - text file; SP130: change Request instructions - scan/upload file; SP140: change Request instructions - scan/fax
E250 | Change request status | MS090: Change request status ; MS110: Full release |  |  |  |  | SP150: Change request status
E260 | Change request completed & account billed | MS100: Change request completed & charged; MS110: Full release |  |  |  |  | SP160: Change request completed & charged

## Sprints
Sprint ID |  | Target release date | Server pts. | Client pts. | Epics | Stories | Notes
SP010 | Account Log-In |  | 11 | 10 | E210: Tool Access
SP020 | Account log-in authenication |  | 17 | 13 | E210: Tool Access
SP030 | URL device detention | 2020-04-17 | 16 | 11 | E210: Tool Access
SP040 | Request Log-In credentials | 2020-05-08 | 19 | 12 | E210: Tool Access
SP050 | Account Profile Maintenance - general | 2020-05-29 | 14 | 16 | E220: Review or Maintain account profile
SP060 | Account Profile Maintenance - billing |  |  |  | E220: Review or Maintain account profile
SP070 | Account Profile Maintenance - change request history |  |  |  | E220: Review or Maintain account profile
SP080 | Account Sitemap |  |  |  | E230: Review sitemap
SP090 | Change Request - add content |  |  |  | E240: Change request creation
SP100 | Change Request - delete/remove content |  |  |  | E240: Change request creation
SP110 | Change Request - update content |  |  |  | E240: Change request creation
SP120 | Change Request instructions - text file |  |  |  | E240: Change request creation
SP130 | change Request instructions - scan/upload file |  |  |  | E240: Change request creation
SP140 | change Request instructions - scan/fax |  |  |  | E240: Change request creation
SP150 | Change request status |  |  |  | E250: Change request status
SP160 | Change request completed & charged |  |  |  | E260: Change request completed & account billed

## Release milestones
Milestone ID | Milestone name | Sequence | No. stories | Stories | Epics | Notes | Attachments
MS010 | Client Log-In | 1 |  |  | E210: Tool Access
MS020 | Client Log-In Authenication | 3 |  |  | E210: Tool Access
MS030 | Client Log-In request credentials | 4 |  |  | E210: Tool Access
MS040 | URL device detention | 2 |  |  | E210: Tool Access
MS050 | Account Profile Maintenance | 5 |  |  | E210: Tool Access
MS060 | Account Sitemap |  |  |  | E230: Review sitemap
MS070 | Change Request | 7 |  |  | E240: Change request creation
MS080 | Change Request instructions | 8 |  |  | E240: Change request creation
MS090 | Change request status | 9 |  |  | E250: Change request status
MS100 | Change request completed & charged | 10 |  |  | E260: Change request completed & account billed
MS110 | Full release | 11 |  |  | E210: Tool Access; E220: Review or Maintain account profile ; E230: Review sitemap ; E240: Change request creation; E250: Change request status ; E260: Change request completed & account billed; :
6

## Facets
Facet ID | Facet | App section | Epics | Sprint | Release seq. no. | Notes
F010 | sign-in/authenicate credentials | AP010: Log in/out | E210: Tool Access | SP010: Account Log-In | 4
F020 | device detection | AP010: Log in/out | E210: Tool Access | SP030: URL device detention | 4
F030 | welcome screen | AP010: Log in/out | E210: Tool Access | SP010: Account Log-In | 3
F040 | two-factor authority, mobile or email | AP010: Log in/out | E210: Tool Access | SP020: Account log-in authenication | 5
F050 | request access credentials | AP010: Log in/out | E210: Tool Access | SP040: Request Log-In credentials
F060 | sign-out/kill session | AP010: Log in/out | E210: Tool Access | SP010: Account Log-In
F070 | user page | AP010: Log in/out | E210: Tool Access | SP010: Account Log-In ; SP050: Account Profile Maintenance - general
F080 | client's contact person, mobile | AP020: account profile | E220: Review or Maintain account profile | SP020: Account log-in authenication; SP050: Account Profile Maintenance - general
F090 | client's mailing address | AP020: account profile | E220: Review or Maintain account profile | SP030: URL device detention
F100 | client's billing method | AP020: account profile | E220: Review or Maintain account profile | SP060: Account Profile Maintenance - billing
F110 | client's request history | AP020: account profile | E220: Review or Maintain account profile | SP070: Account Profile Maintenance - change request history
F120 | sitemap, node tree | AP030: website profile | E230: Review sitemap | SP080: Account Sitemap
F130 | sitemap, dropdown menu | AP040: change request | E230: Review sitemap | SP080: Account Sitemap
F140 | change request type: add | AP040: change request | E240: Change request creation | SP090: Change Request - add content
F150 | change request type: delete/remove | AP040: change request | E240: Change request creation | SP100: Change Request - delete/remove content
F160 | change request type: update | AP040: change request | E240: Change request creation | SP110: Change Request - update content
F170 | request communication method : create text document | AP040: change request | E240: Change request creation | SP120: Change Request instructions - text file
F180 | request communication method : scanned & uploaded file | AP040: change request | E240: Change request creation | SP130: change Request instructions - scan/upload file
F190 | request communication method : scan & fax file | AP040: change request | E240: Change request creation | SP140: change Request instructions - scan/fax
F200 | change request status | AP050: change request approval | E250: Change request status | SP150: Change request status
F210 | Proof Approval status | AP050: change request approval | E250: Change request status | SP150: Change request status
F220 | Change request posted live | AP050: change request approval | E250: Change request status | SP150: Change request status ; SP160: Change request completed & charged
F230 | Client's billing method charged | AP060: change requested posted | E260: Change request completed & account billed | SP160: Change request completed & charged
F240 | invoice generated and available for download | AP060: change requested posted | E260: Change request completed & account billed | SP060: Account Profile Maintenance - billing; SP160: Change request completed & charged

## App sections
App ID | App name | Facets
AP010 | Log in/out | sign-in, device connectin, welcome, two-factor authority
AP020 | account profile | company name, contact info,mailing info, mobile info, billing method, request history
AP030 | website profile | navigation menu/categories, subcategories, pages
AP040 | change request | website profile info, request type: add, delete/remove, update; communication method create text document, scanned & uploaded request, scan & fax
AP050 | change request approval | request indicated as complete and approval required; requested change approved
AP060 | change requested posted | approved changes are posted live; account billing method is charged; invoice available